## Product Backlog
EZTracker Plugin
Release Projections |  |  | Requirement |  | Empirical PERT Calculations |  |  |  |  | P Scope | ML Scope | O Scope
|  |  | Improvement |  |  | Actual | Sprints | Actual | Plan | Remain | Remain | Remain
2021-03-14 | Project start |  | Maintenance |  | Sprint | Velocity | Remain | Burn | Burn | 17 | 9 | 3
7 | Sprint length (days) |  | Overhead |  | Start | 6 | 6 | 58 | 58 | 102 | 54 | 18
2 | Release 1 sprints (#) |  |  |  | 1 | 10 | 5 | 48 | 48.3333 | 85 | 45 | 15
0 | Release 1 release sprint length (days) |  |  |  | 2 | 12 | 4 | 36 | 38.6667 | 68 | 36 | 12
2021-03-28 | Release 1 date |  |  |  | 3 | 17 | 3 | 19 | 29 | 51 | 27 | 9
2 | Release 2 sprints (#) |  |  |  | 4 | 11 | 2 | 8 | 19.3333 | 34 | 18 | 6
0 | Release 2 release sprint length (days) |  |  |  | 5 | 5 | 1 | 3 | 9.6667 | 17 | 9 | 3
2021-04-11 | Release 2 date |  |  |  | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0
2 | Release 3 sprints (#)
0 | Release 3 release sprint length (days)
2021-04-25 | Final release
EZTracker Plugin Product Backlog | [5 empty] | Running | Sprint | Release | Release
ID | Title | Description | Acceptance Criteria | Type | Size | Total | Completed | Dates | Goals
A1a1 | Open plugin on shapefile | As a State Health Official, I am assessing spatially correlated data in my counties. Because of this, I need to be able to see similarities and differences between the counties quickly. I want to do this by clicking on the county I want to analyze. | When I: open the plugin I can: select the layer I want to work with by setting it as my active layer | Requirement | 1 | 1 | 1
A1a2 | Attribute field name autofill | Drop down list appears containing all numerical attributes from the selected layer | I see: a place to enter the range and select the attribute | Requirement | 2 | 3 | 1
A1a3 | Create select portion of tool | The tool can select different features within the layer | I can: interact with the map by selecting polygons | Requirement | 5 | 8 | 1
A1a4 | Data Range default | Create default starting point for date range | I see: a place to enter the range and select the attribute | Requirement | 1 | 9 | 1
A1a5 | Enter a Data Range | Allows the user to input their own numerical data range | I see: a place to enter the range and select the attribute | Requirement | 1 | 10 | 1
X1 | Release 1 presentation | ... | ... | Overhead | 3 | 13 | 2 | 2021-03-28 | Release 1: User interface and key computation
A1b1 | Allow reselction of Attribute | I want to be able to easily change my attribute value range for comparison because not all counties are the same. In some cases I may want to see counties that are very close in infection rate, while in other cases I may want to look at a wider range. | When I: choose or change the attribute I see: the results updated in the map | Requirement | 3 | 16 | 2
A1b2 | Allow reselction of range | Allows the user to update their range and keep working | When I: change the value range I see: the updated results in the map | Requirement | 5 | 21 | 2
A1b3 | Invalid Range | Ensure the user is unable to give the tool an invalid range | I see: a message displaying whether the range is valid or not | Requirement | 1 | 22 | 2
A1b3 | Update layer | Shows the results of the selection and range on the map | I see: the results updated in the map | Requirement | 8 | 30 | 3
A1a8 | Multiple Polygons | Allows the user to select more than one feature for comparison | When I: click multiple polygons I see: a union of results that would appear from each individual polygon given the current range | Improvement | 3 | 33 | 3
A1a7 | Color correct polygons | Polygons that fall within the data range of the selected polygon are highlighted on the map | When I: click on a polygon I see: other similar polygons highlighted | Requirement | 5 | 38 | 3
A1c2 | Ability to re-run plugin | Allows the user to select different ranges and features without rerunning the plugin | When I: select a new feature or polygon, the tool continues working | Requirement | 1 | 39 | 3
X2 | Release 2 Presentation | ... | ... | Overhead | 3 | 42 | 4 | 2021-04-11 | Release 2: Mapping and error model
A1c1 | Ability to save output | When I find an interesting comparison while interacting with the data, I want to be able to save it as a new layer for later | I see: a button that allows me to save my findings as a .qml file (QGISsymbology file) | Requirement | 8 | 50 | 4
B2a1 | Metadata | ... | ... | Requirement | 1 | 51 | 5
B2a2 | Product help | ... | ... | Requirement | 1 | 52 | 5
X3a | Final presentation | ... | ... | Overhead | 3 | 55 | 5 | 2021-04-25 | Final release: complete package
X3b | User’s manual | ... | ... | Overhead | 3 | 58 | 6
Formulas:
Release Projections = A4+(A5*A6)+[Release Projections, row above]
Note on A2: Instructions: Update the portion in <> with your product's name.
Note on A4: Instructions (not required): Insert the project start date.
Note on A5: Instructions (not required): Enter the sprint length, in multiples of 7 days per week of sprint.
Note on G5: Instructions: Enter the scrum team's conservative estimate of how many story points they think they can accomplish the first sprint. This cell will be ignored as soon as there is actual velocity data from the first sprint.
Note on I5: Instructions: If the product owner has a target point in the product backlog, update this cell to point to the cell in column G of the last backlog item included in the scope of the project. (This template provides an example of how you would point to PBI 0018, if that were the target.)
Note on A6: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A7: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A9: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A10: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A12: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A13: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A18: Instructions: Update the portion in <> with your product's name.
Note on A19: Instructions: Enter the ID of the product backlog item (PBI). The ID usually reflects when it was entered in the system, not the priority. The order of the PBIs indicates the priority. This applies to all cells in this column.
Note on B19: Instructions: Enter the title of the product backlog item. Applies to all cells in this column.
Note on C19: Instructions: Enter the product backlog item description. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on D19: Instructions: Enter the product backlog item acceptance criteria. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on E19: Instructions: Select what type of product backlog item this is (Applies to all cells in this column): Requirement: Typically a user story--work that needs to be done to generate functionality for the user. Improvement: Action items from the sprint retrospective. Maintenance: Development work that neesd to be done on the system, but doesn't create new functionality.. Overhead: Non-development work that needs to be done, but doesn't add direct value to the user.
Note on F19: Instructions: Enter the Fibonacci size estimate assigned by the development team. Applies to all cells in this column.
Note on H19: Instructions: Enter the number of the sprint when the PBI was completed (done).Enter whole numbers to match the format of what appears in F6:F15 above. Applies to all cells in this column.
Note on I19: Instructions (optional): Update any cell below to point to the date generated in A4:A14 indicating the projected release date. Note: This may change as velocity changes.
Note on J19: Instructions (optional): Update <> with the actual release goal.